## Initiation
Task Name | Duration (in days) | Start Date | End Date | Status
Project Initiation
Pitch Night Meeting | 0 | 2022-05-16 | 2022-05-16 | Completed
Project Pitch | 0 | 2022-05-23 | 2022-05-23 | Completed
Meeting 2 | 0 | 2022-05-24 | 2022-05-24 | Completed
Client Letter | 1 | 2022-05-25 | 2022-05-26 | Completed
Team Charter | 1 | 2022-05-25 | 2022-05-26 | Completed
Project Charter | 1 | 2022-05-26 | 2022-05-27 | Completed
IP Contract Between Client and Team Members | 0 | 2022-05-31 | 2022-05-31 | Completed
IP Contract Between Team Members | 0 | 2022-05-31 | 2022-05-31 | Completed
Project Plan | 1 | 2022-05-27 | 2022-05-28 | Completed
Web Search and Rationale Report | 1 | 2022-05-29 | 2022-05-30 | Completed
Project Summation Slides | 1 | 2022-05-29 | 2022-05-30 | Completed
Market Analysis | 1 | 2022-05-30 | 2022-05-31 | Completed
Client Sign-off document | 0 | 2022-05-30 | 2022-05-30 | Completed
Meeting 3 | 0 | 2022-05-30 | 2022-05-30 | Completed

## Iteration 1
Task Name | Duration (in days) | Start Date | End Date | Status
Analysis
Agile Iteration Plan | 1 | 2022-06-01 | 2022-06-02 | Pending
Use Case Diagrams | 1 | 2022-06-01 | 2022-06-02 | Pending
Use Case Descriptions | 1 | 2022-06-01 | 2022-06-02 | Pending
Domain Class Diagram | 1 | 2022-06-01 | 2022-06-02 | Pending
System Sequence Diagrams | 1 | 2022-06-01 | 2022-06-02 | Pending
Statechart Diagrams | 1 | 2022-06-01 | 2022-06-02 | Pending
Design
Design Class Diagram | 1 | 2022-06-02 | 2022-06-03 | Pending
Design level Sequence Diagrams | 1 | 2022-06-02 | 2022-06-03 | Pending
Navigation Diagram(s) | 1 | 2022-06-02 | 2022-06-03 | Pending
User Interface Prototype | 1 | 2022-06-02 | 2022-06-03 | Pending
Entity Relationship Diagram (ERD) | 1 | 2022-06-02 | 2022-06-03 | Pending
Data Dictionary with field level definitions or Glossary | 1 | 2022-06-02 | 2022-06-03 | Pending
Development
Create databases for admin portal menu/advertisement module | 2 | 2022-06-03 | 2022-06-05 | Pending
Build admin portal menu/advertisement module UI | 4 | 2022-06-05 | 2022-06-09 | Pending
Build admin portal menu/advertisement module APIs | 5 | 2022-06-05 | 2022-06-10 | Pending
Testing
Create test plan | 1 | 2022-06-10 | 2022-06-11 | Pending
Create test cases | 1 | 2022-06-10 | 2022-06-11 | Pending
Execute test cases | 1 | 2022-06-10 | 2022-06-11 | Pending
Record defects | 1 | 2022-06-10 | 2022-06-11 | Pending
Fix defects | 2 | 2022-06-12 | 2022-06-14 | Pending
Reporting
Meeting 1 | 0 | 2022-06-06 | 2022-06-06 | Pending
Meeting 2 | 0 | 2022-06-13 | 2022-06-13 | Pending

## Iteration 2
Task Name | Duration (in days) | Start Date | End Date | Status
Analysis
Agile Iteration Plan | 1 | 2022-06-15 | 2022-06-16 | Pending
Use Case Diagrams | 1 | 2022-06-15 | 2022-06-16 | Pending
Use Case Descriptions | 1 | 2022-06-15 | 2022-06-16 | Pending
Domain Class Diagram | 1 | 2022-06-15 | 2022-06-16 | Pending
System Sequence Diagrams | 1 | 2022-06-15 | 2022-06-16 | Pending
Statechart Diagrams | 1 | 2022-06-15 | 2022-06-16 | Pending
Design
Design Class Diagram | 1 | 2022-06-16 | 2022-06-17 | Pending
Design level Sequence Diagrams | 1 | 2022-06-16 | 2022-06-17 | Pending
Navigation Diagram(s) | 1 | 2022-06-16 | 2022-06-17 | Pending
User Interface Prototype | 1 | 2022-06-16 | 2022-06-17 | Pending
Entity Relationship Diagram (ERD) | 1 | 2022-06-16 | 2022-06-17 | Pending
Data Dictionary with field level definitions or Glossary | 1 | 2022-06-16 | 2022-06-17 | Pending
Development
Create databases for store front module | 3 | 2022-06-18 | 2022-06-20 | Pending
Build store front module UI | 6 | 2022-06-21 | 2022-06-26 | Pending
Build store front module APIs | 7 | 2022-06-21 | 2022-06-27 | Pending
Testing
Create test plan | 1 | 2022-06-27 | 2022-06-28 | Pending
Create test cases | 1 | 2022-06-27 | 2022-06-28 | Pending
Execute test cases | 1 | 2022-06-27 | 2022-06-28 | Pending
Record defects | 1 | 2022-06-27 | 2022-06-28 | Pending
Fix defects | 2 | 2022-06-28 | 2022-06-30 | Pending
Reporting
Meeting 1 | 0 | 2022-06-20 | 2022-06-20 | Pending
Meeting 2 | 0 | 2022-07-04 | 2022-07-04 | Pending

## Iteration 3
Task Name | Duration (in days) | Start Date | End Date | Status
Analysis
Agile Iteration Plan | 1 | 2022-07-05 | 2022-07-06 | Pending
Use Case Diagrams | 1 | 2022-07-05 | 2022-07-06 | Pending
Use Case Descriptions | 1 | 2022-07-05 | 2022-07-06 | Pending
Domain Class Diagram | 1 | 2022-07-05 | 2022-07-06 | Pending
System Sequence Diagrams | 1 | 2022-07-05 | 2022-07-06 | Pending
Statechart Diagrams | 1 | 2022-07-05 | 2022-07-06 | Pending
Design
Design Class Diagram | 1 | 2022-07-06 | 2022-07-07 | Pending
Design level Sequence Diagrams | 1 | 2022-07-06 | 2022-07-07 | Pending
Navigation Diagram(s) | 1 | 2022-07-06 | 2022-07-07 | Pending
User Interface Prototype | 1 | 2022-07-06 | 2022-07-07 | Pending
Entity Relationship Diagram (ERD) | 1 | 2022-07-06 | 2022-07-07 | Pending
Data Dictionary with field level definitions or Glossary | 1 | 2022-07-06 | 2022-07-07 | Pending
Development
Create databases for order management module | 3 | 2022-07-08 | 2022-07-10 | Pending
Build order management module UI | 5 | 2022-07-11 | 2022-07-15 | Pending
Build order management module APIs | 6 | 2022-07-14 | 2022-07-20 | Pending
Testing
Create test plan | 1 | 2022-07-20 | 2022-07-21 | Pending
Create test cases | 1 | 2022-07-20 | 2022-07-21 | Pending
Execute test cases | 1 | 2022-07-20 | 2022-07-21 | Pending
Record defects | 1 | 2022-07-20 | 2022-07-21 | Pending
Fix defects | 2 | 2022-07-22 | 2022-07-24 | Pending
Reporting
Meeting 1 | 0 | 2022-07-11 | 2022-07-11 | Pending
Meeting 2 | 0 | 2022-07-18 | 2022-07-18 | Pending
Meeting 3 | 0 | 2022-07-25 | 2022-07-25 | Pending